## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered
Sprint 1(Constructing Diagrams) |  | Story Points (in 4 days)
User Stories |  | 2 |  |  | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
Test Cases |  | 2
Context Diagram |  | 1
Uses Cases Diagram |  | 2
Sequence Diagram |  | 1
Database design |  | 2
Class Diagram |  | 1
Total |  | 11 | Velocity Sprint 1 | 9
Sprint 2
ERD Model |  | 2
Admin Add Product Class |  | 2
Cart Page Class |  | 3
Admin Add Product Form HTML |  | 2
Total |  | 9 | Velocity Sprint 2 | 9
Sprint 3 (Backlog sprint)
Registration |  | 2
Ordering Process |  | 3
Total |  | 5 | Velocity Sprint 3 | 5
Sprint 4 (Backlog Process)
Sign in page HTML |  | 3 |  |  | Note: this user story wasn't delivered in Sprint 4 since the team didn't have time to complete it
Total |  | 3 | Velocity Sprint 4 | 3
Sprint 5 (Backlog Sprint and Process 2)
Sign In Page Class |  | 4
Home Page Class of Products |  | 4
Home Page HTML |  | 4
Cart Page HTML |  | 4
Cart Page PHP |  | 4
Total |  | 26 | Velocity Sprint 4 | 20
Total Story Points |  | 54 | Average Velocity | 9.2 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Traditional
Burndown Chart
Sprint | Remaining Story Points
0 | 54
1 | 45
2 | 36
3 | 31
4 | 28
5 | 8
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 54 | 9
2 | 45 | 9
3 | 36 | 5
4 | 31 | 20
5 | 11 | 0
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 54 | 9
2 | 45 | 9
3 | 36 | 5
4 | 31 | 20
5 | 11 | 0